SADHGURU ENGLISH → TELUGU DUB

Voice Cloning + Lip-Sync — Project Plan

Goal:  take an English talk and produce a Telugu version — his voice, his mouth moving correctly, the original music and ambience intact underneath.

# 1.  The Pipeline

| # | Stage | What it does |
| --- | --- | --- |
| 1 | Separate | Split voice from background — music/ambience kept untouched |
| 2 | Transcribe | Whisper large-v3 transcribes the isolated voice |
| 3 | Translate | Dubbing-style Telugu: meaning over literal structure, tone kept, each line sized to fit the original timing |
| 4 | Voice | Sadhguru's own voice model speaks the Telugu lines |
| 5 | Fit timing | Stretch / compress / borrow pause so each line lands on his original timing — never starts early |
| 6 | Mix | Telugu speech laid over the untouched background |
| 7 | Lip-sync | Regenerate the mouth to match the Telugu audio |
| 8 | Final video | His face, his voice, Telugu speech, lips matching, original background intact |

Stages 1, 2, 3, 5, 6 and 8 are standard audio/video engineering. Stages 4 (his voice) and 7 (lip-sync) decide whether the result is convincing — the rest of this document is about those two.

TIMELINE: 3–5 weeks end to end, from a standing start to one finished clip. Two tracks run in parallel rather than in sequence — see Section 5.

# 2.  Stage 4 — Sadhguru's Voice, in Telugu

## Two approaches

| Approach | Timeline | What you get |
| --- | --- | --- |
| Zero-shot cloning | Same day | A 10–15 s reference clip is enough. Captures his timbre. Does not capture his delivery — the pauses, the emphasis, the timing that makes him sound like him rather than a similar voice. |
| Fine-tuned model | 2–3 weeks | Trained on hours of his own recordings. Captures timbre and delivery. The real target. |

## Fine-tune data requirement

| Training audio | Result |
| --- | --- |
| 1–3 hours | Workable, rough on words unlike the training set |
| 5–20 hours | The target — clean, single-speaker, accurately transcribed |
| 30+ hours | Studio-grade |

## Plan

- Collect 5–20 hours of clean English audio — long single-camera talks, background/audience stripped out.  (2–4 days)

- Transcribe and hand-correct the training transcripts — this is the ceiling on fine-tune quality.  (2–3 days)

- Fine-tune a voice model (F5-TTS-based, Indic-capable) on that English audio, on a GPU with real memory (A100-class).  (1–2 days)

- Generate Telugu with the fine-tuned model and evaluate it by ear — a native Telugu speaker, blind, scoring pronunciation, pitch and rhythm separately.  (1–2 days)

- Decide: convincing → that's the production voice. Not convincing → the model still works well for English, and Telugu falls back to zero-shot cloning while the cross-lingual approach is refined.

CONSENT: training a model that can make him say sentences he never spoke is a bigger step than dubbing his own words. Proceed only with Isha's participation or explicit written consent, and keep the resulting model access-controlled.

# 3.  Stage 7 — Lip-Sync

TIMELINE: 3–5 days for validation. Folding lip-sync into a full video happens once a voice is ready to pair it with.

- Rent a GPU for testing rather than provisioning permanent infrastructure — a 24 GB-class card (RTX 4090 / L40S / A100) is enough.

- Use an open lip-sync model with strong visual fidelity (LatentSync-class) as the primary approach.

- Validate on a close-up clip with his beard visible first — facial hair is the known hard case for this class of model.

- Add a face-restoration pass if needed to sharpen the regenerated mouth region.

- Keep a hosted lip-sync API as a parallel comparison point, for a quality ceiling without standing up infrastructure.

- Only run lip-sync on shots where his face is actually on camera — cutaways pass through untouched.

Lip-sync is the most compute-intensive stage by a wide margin — prove it on one short, hard clip before spending time or money on a full video.

# 4.  Requirements

| Category | What's needed |
| --- | --- |
| Data | • 5–20 hours of clean English Sadhguru audio, for the voice model • Accurate, hand-checked transcripts of that audio • A short test clip with his face visible, including a beard close-up |
| Compute | • Ordinary CPU is enough for transcription, translation, timing and mixing • A 24 GB-class GPU (rented) for the voice fine-tune and lip-sync testing |
| Accounts | • A translation API account, for the dubbing-style translation step • A TTS account or self-hosted model, for the zero-shot voice / fallback • A GPU rental account, for the fine-tune and lip-sync runs • Optionally, a hosted lip-sync API, as a comparison point |
| People | • A native Telugu speaker for every listening decision • Sign-off from Isha (or explicit consent) before wider use |

# 5.  Plan & Timeline

Total: 3–5 weeks  from a standing start to one finished clip. Two tracks run in parallel — the voice model work does not wait on the audio pipeline.

| # | Step | Duration | Depends on |
| --- | --- | --- | --- |
| 1 | Audio pipeline | ~1 week | Nothing — starts immediately |
| 2 | Collect + transcribe training audio | ~1 week (overlapped) | Nothing — runs alongside step 1 |
| 3 | Fine-tune, test in Telugu, go/no-go | ~1 week | Step 2 finished |
| 4 | GPU lip-sync beard test | 3–5 days (overlapped) | Nothing — only needs the test clip |
| 5 | Combine + full review | ~1 week | Steps 1, 3, 4 all finished |

## Where the timeline moves

- Compresses to ~2 weeks — if the zero-shot voice is judged good enough on review, the fine-tune step is skipped.

- Stretches by ~1 week — if the fine-tuned voice fails its Telugu listening test and needs a second iteration. The one genuinely open-ended part of the plan.

Sadhguru Telugu Dub — Project Plan